## Master Schedule
Feature | Story | Status | EMD | BMD | Progress | Week 1 (24/6 - 28/6) | Week 2 (1/7 - 5/7) | Week 3 (8/7 - 12/7) | Week 4 (15/7 - 19/7) | Week 5 (22/7 - 26/7) | Week 6 (29/7 - 2/8) | Note
User Management (Khuong, TAnh) | SRS, Usecase, ERD for User Management | Done | 0 | 24 | 100%
| [FE] Component Library | Done | 3 | 4.5 | 100% | 3
| [BE] Implement story Create/Update User/Active/Deactive User/Delete (CUD) | Done | 6 | 8.5 | 100% | 2 | 4
| [BE] Implement story Role-Permission, Authenticate & Authorize User | Done | 6 | 4.25 | 100% | 2 | 4
| [FE] UI Implementation | In-Progress | 11.25 | 11.25 | 0% |  |  | 4 | 4 | 3
| [FE] Implement story Retrieve Users [List + Paging] & [Search + Filter] (R) | Not-Start | 11.25 | 11.25 | 0% |  |  | 4 | 4
| Fix bug & Cover Task | Not-Start | 13 | 0 | 0% |  |  |  |  | 5 | 8
Feature | Story | Status | EMD | BMD | Progress | Week 1 (24/6 - 28/6) | Week 2 (1/7 - 5/7) | Week 3 (8/7 - 12/7) | Week 4 (15/7 - 19/7) | Week 5 (22/7 - 26/7) | Week 6 (29/7 - 2/8) | Note
Syllabus Management (NHuy, Ban) | SRS, Usecase, ERD for Syllabus Management | Done | 0 | 24 | 100%
| [FE] Component Library for Syllabus Management | Done |  |  | 100% | 2
| [FE] Implement story Create Syllabus/Save as Draft | Not-Start | 2.5 | 9 | 0% |  |  | 2.5
| [FE] Implement story Edit Syllabus | Not-Start |  |  | 0% |  |  | 2.5
| [FE] Implement story Get List of Syllabuses/Pagination Syllabus | Not-Start |  |  | 0% |  |  | 1.5
| [FE] Implement story Delete Syllabus | Not-Start |  |  | 0% |  |  | 1.5
| [FE] Implement story Duplicate Syllabus/Import Files | Not-Start |  |  | 0% |  |  |  | 4
| [FE] Implement story Search & Filter Syllabus | Not-Start |  |  | 0% |  |  |  | 4
| [FE] Implement story Active/Deactive Syllabus | Not-Start | 2 | 6.5 | 0% |  |  |  |  | 2
| [FE] Implement story View Syllabus Detail | Not-Start |  |  | 0% |  |  |  |  | 2
| [BE] Implement story CRUD Metadata Output Standard/Delivery Type, Training Syllabus Material | Pending | 7 | 10.5 | 100% | 3 | 4
| [BE] Implement story CRUD Syllabus | Pending |  |  | 100% | 3 | 4
| Fix bug & Cover Task | Not-Start | 12 | 0 | 0% |  |  |  |  | 4 | 8
Feature | Story |  | EMD | BMD | Progress | Week 1 (24/6 - 28/6) | Week 2 (1/7 - 5/7) | Week 3 (8/7 - 12/7) | Week 4 (15/7 - 19/7) | Week 5 (22/7 - 26/7) | Week 6 (29/7 - 2/8) | Note
Training Program Management (Hoàng Ân, Xuân Mạnh) | SRS, Usecase, ERD for training program management | Done | 0 | 0 | 100%
| (FE) Implement UI for Import, Create, Update, Duplicate | In-Progress | 7 | 4 | 0% |  | 3 | 4
| (BE) Implement story Training program CIUD Management | Done | 3 | 3 | 100% | 3
| (FE) Implement UI for Get list, paging, search, filter | Not-Start | 7.5 | 4 | 0% |  |  |  | 3 | 1
| (BE) Implement story Training material CRUD Management | Done | 2.5 | 0 | 100% | 2.5
| (FE) Implement UI for getting Detail Training program information | In-Progress | 7 | 1.25 | 20% |  | 3 | 4
| (FE) Implement UI for delete, active, deactive program | Not-Start |  |  | 0% |  |  |  | 3 | 1
| (BE) Implement story delete, active, deactive program | Done | 4.5 | 4.5 | 100% | 2.5 | 2
| Fix bug & Cover Task | Not-Start | 11.5 | 0 | 0% |  |  |  | 1.5 | 2 | 8
Feature | Story | Status | EMD | BMD | Progress | Week 1 (24/6 - 28/6) | Week 2 (1/7 - 5/7) | Week 3 (8/7 - 12/7) | Week 4 (15/7 - 19/7) | Week 5 (22/7 - 26/7) | Week 6 (29/7 - 2/8) | Note
Class Management (THuy, Tung) | SRS, Usecase, ERD for class management | Done | 0 | 0 | 100%
| [FE] Implement story List of Class, Pagination, Filter, Sort | Not-Start | 7.5 | 5 | 0% |  |  | 4 | 1
| [BE] Implement story Delete/Active/Deactive | Pending | 5 | 5 | 100% | 2.5 | 2.5
| [BE] Implement story Create classs & Import file | Pending | 5 | 2 | 100% | 2.5 | 2.5
| [FE] Implement story View class detail | Not-Start | 5 | 0 | 0% |  |  | 4 | 1
| [FE] General info, attendee general info, other info (others tab) | Not-Start | 8 | 0 | 0% |  |  |  | 4 | 4
| [BE] Change training program, add/remove syllabus, add activity, select trainer, location | Pending | 6 | 0 | 100% | 3 | 3
| Fix bug & Cover Task | Not-Start | 14 | 0 | 0% |  |  |  | 2 | 4 | 8
|  | Total Progress Actual |  |  | 43.78%
| Done | 11
| Not-Start | 18
| In-Progress | 3
| Pending | 5