## FSA_FPT_Sprint1_Info_HuyNN_BanB
| Planning - Forecast |  |  |  | Actual
[5 empty] | PIC | Point | Release Point | Total ID
| Point Total |  | Points |  | HuyNN
| Working days of developer |  | Coding (day) |  | BanBP
| Sprint 1 |  |  |  | Total
| (Forecast - Plan) Point Total |  | Points
| Working days of developer | 10 | Coding (day)
Total
# | Module | Story | Description | Sprint | Status | PIC | DueDate | Point | Ticket Jira
1 | GROUP WORK | [FE] Component Library | Create a common asset library for the whole project | 1 | Open | HuyNN | 28-Jun-2024
2 | GROUP WORK | [FE] Component Library | Create a common asset library for the whole project | 1 | Open | BanBP | 28-Jun-2024
3 | Create Syllabus | [FE][SyllabusManagement_1] - Create/Save as draft Syllabus | Implement UI for Create Syllabus/Save as Draft story | 1 | Open | HuyNN | 04-Jul-2024
4 | Update Syllabus | [FE][SyllabusManagement_4] - Edit Syllabus | Implement UI for Edit Syllabus story | 1 | Open | HuyNN | 04-Jul-2024
5 | Delete Syllabus | [FE][SyllabusManagement_5] - Delete Syllabus | Implement UI for Delete Syllabus story | 1 | Open | HuyNN | 04-Jul-2024
6 | Read Syllabus | [FE][SyllabusManagement_9] - Get List of Syllabuses | Implement UI for Get List of Syllabus story | 1 | Open | BanBP | 04-Jul-2024
7 | Read Syllabus | [FE][SyllabusManagement_5] - Pagination Syllabus | Implement Syllabus Pagination | 1 | Open | BanBP | 04-Jul-2024