## FSA_FPT_Sprint2_Info_HuyNN_BanB
| Planning - Forecast |  |  |  | Actual
[5 empty] | PIC | Point | Release Point | Total ID
| Point Total | 16 | Points |  | HuyNN | 8
| Working days of developer | 20 | Coding (day) |  | BanBP | 8
| Sprint 2 |  |  |  | Total | 16
| (Forecast - Plan) Point Total | 16 | Points
| Working days of developer | 20 | Coding (day)
Total
# | Module | Story | Description | Sprint | Status | PIC | DueDate | Point
1 | Create Syllabus | [FE] Implement story Create Syllabus/Save as Draft |  | 2 | Open | HuyNN | 2024-07-10 | 2.5
2 | Update Syllabus | [FE] Implement story Edit Syllabus |  | 2 | Open | BanBP | 2024-07-10 | 2.5
3 | Read Syllabus | [FE] Implement story Get List of Syllabuses/Pagination Syllabus |  | 2 | Open | HuyNN | 2024-07-11 | 1.5
4 | Delete Syllabus | [FE] Implement story Delete Syllabus |  | 2 | Open | BanBP | 2024-07-11 | 1.5
5 | Create Syllabus | [FE] Implement story Duplicate Syllabus/Import Files |  | 2 | Open | HuyNN | 2024-07-18 | 4
6 | Read Syllabus | [FE] Implement story Search & Filter Syllabus |  | 2 | Open | BanBP | 2024-07-18 | 4