## Master Schedule
Feature | Story | Status | EMD | BMD | Progress | Week 1 (24/6 - 28/06) | Week 2 (1/7 - 5/7) | Week 3 (8/7 - 12/7) | Week 4 (15/7 - 19/7) | Week 5 (22/7 - 26/7) | Week 6 (29/7 - 2/8) | Week 7 (3/8 - 7/8) | Week 8 (21/11-25/11) | Note
User Management | Create User | Not-Start
| Login (Authenticate User), LogOut | Not-Start
| Import & Export User | Not-Start
| Forget Pass | Not-Start
| View List of User | Not-Start
| Retrieve User [List + Paging] | Not-Start
| Search + Filter User | Not-Start
| Update/Active/Deactive/Delete | Not-Start
| Role-Permission, Authorize User | Not-Start
| Add new Roles | Not-Start
| Fix Bug & Cover Task | Not-Start
Syllabus Management | [FE] Build base frontend | In-Progress |  |  |  | 3
| [BE] Build base backend | In-Progress |  |  |  | 3
| [BE] API create syllabus | In-Progress |  |  |  | 3
| [FE] UI Import Syllabus | In-Progress |  |  |  | 1
| [FE] Syllabus Table UI & Extra UI | In-Progress |  |  |  | 4
| [BE][FE] Import Syllabus & Validate data | Not-Start | [5 empty] | 2
| [BE] Duplicate Syllabus | Not-Start |  |  |  |  | 2
| [BE] Edit syllabus | Not-Start |  |  |  |  | 4
| [BE] Active/Deactive Syllabus | Not-Start |  |  |  |  | 1
| [BE] Delete Syllabus | Not-Start |  |  |  |  | 1
| [BE] List of Syllabuses & Pagination | Not-Start |  |  |  |  | 2
| [FE] Fetch API List & Paging Render data | Not-Start |  |  |  |  | 2
| [BE] View Syllabus Detail | Not-Start | [5 empty] | 2
| [BE] Search & Filter | Not-Start |  |  |  |  | 2
| [FE] View Syllabus Detail & Fetch API | Not-Start | [5 empty] | 7
| [BE][FE] CRUD Training Syllabus Material | Not-Start | [5 empty] | 1
| [BE][FE] CRUD Metadata Output Standard | Not-Start | [5 empty] | 1
| [BE][FE] CRUD Metadata Delivery Type | Not-Start | [5 empty] | 1
| [FE] UI Create/Save as draft Syllabus | Not-Start | [6 empty] | 5
| Fix bug & Cover Task | Not-Start | [7 empty] | 30
| Story | Not-Start
| Implement story Create, Import | Not-Start
| Implement story Getlist/Sort, Search/Filter | Not-Start
| Implement story Update, Delete | Not-Start
| Implement story Duplicate, Activate/Deactivate | Not-Start
| Implement story Training material CRUD | Not-Start
| Implement story Get detail | Not-Start
Class Management | Implement story Download all training material (foldered structure), Export | Not-Start
| Fix bug & Cover Task | Not-Start
| View class detail | Not-Start
| Create class | Not-Start
| Update general infor of class | Not-Start
| Class's budget management | Not-Start
| Class's training program management | Not-Start
| List of class | Not-Start
| Active/De-active | Not-Start
| Delete | Not-Start
Import file
Fix bug & Cover Task
0
43
| Done | 5
| Not-Start | 0
In-Progress
Pending