## Class Management
| Planning - Forecast |  |  |  | Actual
[5 empty] | PIC | Point | Release Point | Total ID
| Point Total |  | Points |  | Trần Đình Đăng Khoa | 0 | 0 | 0
| Working days of developer |  | Coding (day) |  | Trương Thuận Hưng | 0 | 0 | 0
Sprint 1
| (Forecast - Plan) Point Total | 33.5 | Points
| Working days of developer | 8 | Coding (day) |  | Total | 0 | 0 | 0
| (Forecast - Plan) AVG points/Member/Sprint | 4.1875 | Points
[6 empty] | Total |  | 33.5
# | Module | Story | Description | Sprint | Status | PIC | DueDate | Point | Ticket Jira
1 | Class Management | [Design_Database] | Create Entity-Relationship Diagram (ERD) and Relation Schema | 1 | Pending |  | 04/07/2024 | 2
2 | Class Management | [ClassManagement_01] View class detail | Build basic design & common components of View Class Detail | 1 | Pending |  | 04/07/2024 | 2
3 | Class Management | [ClassManagement_01] View class detail | Build structure for BE & API for getting Class Detail | 1 | Pending |  | 04/07/2024 | 2
4 | Class Management | [ClassManagement_01] View class detail | Build View Class Detail UI | 1 | Pending |  | 04/07/2024 | 2
5 | Class Management | [ClassManagement_02] Create Class | Build basic design & common components of Create Class | 1 | Pending |  | 04/07/2024 | 2
6 | Class Management | [ClassManagement_02] Create Class | Build Create Class UI | 1 | Pending |  | 04/07/2024 | 4
7 | Class Management | [ClassManagement_02] Create Class | Build structure for BE & API for Create Class | 1 | Pending |  | 04/07/2024 | 2
8 | Class Management | [ClassManagement_02] Create Class | Get list Training Program and Get by Id BE | 1 | Pending |  | 04/07/2024 | 1
9 | Class Management | [ClassManagement_02] Create Class | Validate form of Create Class | 1 | Pending |  | 04/07/2024 | 1.5
10 | Class Management | [ClassManagement_02] Create Class | Option get Attendee list FE | 1 | Pending |  | 04/07/2024 | 1
11 | Class Management | [ClassManagement_03] Update General Infor Of Class | Build basic design & common components of Update General Infor Of Class | 1 | Pending |  | 04/07/2024 | 2
12 | Class Management | [ClassManagement_03] Update General Infor Of Class | Build Update General Infor Of Class UI | 1 | Pending |  | 04/07/2024 | 4
13 | Class Management | [ClassManagement_03] Update General Infor Of Class | Build structure for BE & API for Update General Infor Of Class | 1 | Pending |  | 04/07/2024 | 4
14 | Class Management | [ClassManagement_03] Update General Infor Of Class | Validate form of Update General Infor Of Class | 1 | Pending |  | 04/07/2024 | 4

## Training Program Management
| Planning - Forecasst |  |  |  | Actual
[5 empty] | PIC | Point | Release Point | Total ID
| Point Total |  | Points
| Working days of developer |  | Coding (day)
Sprint 1
| (Forecast - Plan) Point Total | #REF! | Points
| Working days of developer | 8 | Coding (day)
| (Forecast - Plan) AVG points/Member/Sprint | #REF! | Points
[6 empty] | Total |  | #REF!
# | Module | Story | Description | Sprint | Status | PIC | DueDate | Point | Ticket Jira
1 | Training Program Management | [Training Program Management_01]Page UI | Our page's user interface (UI) features a sleek and sophisticated design that immediately captures users' attention. The interface is meticulously created to be visually attractive while also exuding a contemporary and professional appearance. | 1 | Pending
2 | Training Program Management | [Training Program Management_02]View list Training Program API | Write API to view list of Training Program | 1 | Pending
3 | Training Program Management | [Training Program Management_03]Sorting | Write sort all field in table | 1 | Pending
4 | Training Program Management | [Training Program Management_04]Paging API | Write API to paging in view list | 1 | Pending
5 | Training Program Management | [Training Program Management_05]Search API | Write API to search by all field | 1 | Pending
6 | Training Program Management | [Training Program Management_06]Filter | Select options for filter data | 1 | Pending
7 | Create, import | Create | Write API to create a training program | 1 | Pending
8 |  | Import | Write API to import an Excel/CSV file | 1 | Pending
9 | Update, delete | Update | Write API to update a training program | 1 | Pending
10 |  | Delete | Write API to delete a training program | 1 | Pending

## Syllabuses Management
| Planning - Forecast |  |  |  | Actual
[5 empty] | PIC | Point | Release Point | Total ID
| Point Total |  | Points |  | Nhựt | 0 | #VALUE! | 0
| Working days of developer |  | Coding (day) |  | Tân | 0 | #VALUE! | 0
| Sprint 1 |  |  |  | Tiên | 0 | #VALUE! | 0
| (Forecast - Plan) Point Total |  | Points |  |  | 0 | #VALUE! | 0
| Working days of developer | 15 | Coding (day) |  |  | 0 | #VALUE! | 0
| (Forecast - Plan) AVG points/Member/Sprint | 0 | Points
[5 empty] | Total | 0 | #VALUE! | 0
[6 empty] | Total |  | 0
# | Module | Story | Description | Sprint | Status | PIC | DueDate | Point | Ticket Jira
1 | Get List of Syllabuses & Paging | [FE][SyllabusManagement]-Syllabus Table UI |  | 1 | Not-Start
2 |  | [FE][SyllabusManagement]-Extra UI |  | 1 | Not-Start
3 |  | [BE][SyllabusManagement]Build Base Backend |  | 1 | Not-Start
4 |  | [BE][SyllabusManagement]-List Syllabus |  | 1 | Not-Start
5 |  | [BE][SyllabusManagement]-Paging |  | 1 | Not-Start
6 |  | [FE][SyllabusManagement]-Fetch API List & Paging Render data |  | 1 | Not-Start
8 | View Syllabus Detail | [FE][SyllabusManagement]View Syllabus Detail & Fetch API |  | 1 | Not-Start
9 |  | [FE][SyllabusManagement]View Syllabus Detail |  | 1 | Not-Start
10 |  | [FE][SyllabusManagement]View Syllabus Detail |  | 1 | Not-Start
11 |  | [BE][SyllabusManagement]Syllabus Detail |  | 1 | Not-Start
Not-Start
In-Progress
Done

## User Management
| Planning - Forecast |  |  |  | Actual
[5 empty] | PIC | Point | Release Point | Total ID
| Point Total |  | Points |  | Nguyễn Phan Duy Minh | 0 | 0 | 0
| Working days of developer |  | Coding (day) |  | La Thế Thành | 0 | 0 | 0
Sprint 1
| (Forecast - Plan) Point Total | 14 | Points
| Working days of developer | 8 | Coding (day) |  | Total | 0 | 0 | 0
| (Forecast - Plan) AVG points/Member/Sprint | 1.75 | Points
[6 empty] | Total |  | 14
# | Module | Story | Description | Sprint | Status | PIC | DueDate | Point | Ticket Jira
1 | Login Page | [User Management_01]Back End api | The API for validate username, email and password also authenticate user | 1 | Pending |  | 04/07/2024 | 2
2 | Login Page | [User Management_02]Front End page | The UI component display login page, allow using or email and password to . | 1 | Pending |  | 04/07/2024 | 2
3 | Add new users | [User Management_03]Back end add new user api | The API for adding new users includes info such as email, full name, D.O.B, gender, role and status. In addition, must validate input based on the SRS file. | 1 | Pending |  | 04/07/2024 | 2
4 | Add new users | [User Management_04]Front end add new user screen | The UI component display the screen to add new user info from the backend API and must also validate the input data. | 1 | Pending |  | 04/07/2024 | 2
5 | Role Management | [User Management_05]Backend change role API | The API to change user roles based on roles already available in the system | 1 | Pending |  | 04/07/2024 | 2
6 | Role Management | [User Managemen_05]Front end change role screen | The UI component displays the screen to change role of the user | 1 | Pending |  | 04/07/2024 | 4